## ESTIMATED COST
Barangay South Signal Village Web App
Project Duration (months) |  |  |  | 12
PROJECT COST ELEMENTS
Manpower Estimated Cost
Role | Average Salaray (monthly) | Total Salary (12 months) | Count | Total
Project Manager | 50605 | 607260 | 1 | 607260 | https://ph.indeed.com/career/project-manager/salaries
Product Owner | 58500 | 702000 | 1 | 702000 | https://www.payscale.com/research/PH/Job=Product_Owner/Salary
Scrum Master / Developer | 79500 | 954000 | 1 | 954000 | https://www.payscale.com/research/PH/Job=ScrumMaster/Salary
Scrum Member / Laravel Junior Developer | 40000 | 480000 | 2 | 960000 | https://ph.indeed.com/career/documentation-manager/salaries
Documentation Manager | 41059 | 492708 | 1 | 492708 | Laravel Junior Developer Work, Jobs - 25 April, 2023 ¦ Indeed.com Philippines
Total Manpower Cost Estimate |  |  |  | 3715968
Maintenance Estimated Cost
Managed SSL Services | 4999 | yearly |  | 4999 | Managed SSL Service ¦ A Managed SSL Installation and Renewal Service - GoDaddy PH
Website Security (Premuim) | 799 | monthly |  | 9588 | Website Security - Protect Your Site with GoDaddy
Website Backup | 99 | monthly |  | 1188 | Website Backup ¦ Automated and Cloud Based Backups - GoDaddy PH
System Administrator | 30000 | monthly |  | 360000 | Website Administrator Work, Jobs - 25 April, 2023 ¦ Indeed.com Philippines
Maintenace (yearly) |  |  |  | 375775
Hosting and DNS Cost
Hosting w/ DNS protection (36 months) | 12992.72 | every 3 years |  | 12992.72
Indirect Cost
Utilities | Covered by the barangay
Equipments
Administrative Roles
Estimated Project Cost | 4104735.72
Maintenace (yearly) | 375775

## ESTIMATED BENEFIT
Estimated Benefit
Estimated Number of Requests per year | 70000
Estimated revenue from requesting documents | 50
Estimated Average Benefit every year | 3500000

## COST-BENEFIT ANALYSIS
Estimated increase per yer: | 1.1
100 % No Error | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7
Benefit | 3500000 | 3850000 | 4235000 | 4658500 | 5124350 | 5636785 | 6200463.5
Cost | 4104735.72 | 375775 | 375775 | 388767.72 | 375775 | 375775 | 375775
Estimated Savings | -604735.72 | 2869489.28 | 3859225 | 4269732.28 | 4748575 | 5261010 | 5824688.5